BOTTLENECKS IN HYDRO POWER DEVELOPMENT

By Ramesh Chandra, Executive Director (Uttarakhand)

It is now a well recognized fact that availability of electric power is an essential requirement for the development of the nation.  With the fast depleting fossil fuels, the need to increase and shift dependence on hydro power generation for development and prosperity of the nation has become compulsive.  India has a hydro power potential of about 150000 MW besides about 94000 MW of pump storage schemes. As on June 2007 installed capacity of hydro power is 33486 MW. It means we have harnessed the 22.3 percent of the total assessed hydro potential.  The total installed capacity of the India at the end of June 2007 was 134770 MW besides 14637 MW captive generating capacity connected to the grid.  Hydro power is not only cleaner and environment friendly but also provides peak power and system reliability to the grid.  Ideally, the ratio of hydro and thermal has been assessed in India as 40:60 but at the end of June, 2007, the ratio is 27.8 hydro to 72.2 thermal.   During the last two Five Year Plans, much emphasis was given for speedy capacity addition of hydro power but the results were not encouraging.  During the 10th Five Year Plan, 14393 MW hydro power capacity addition plan was  made but even after best efforts by the all concerned 7900 MW capacity could be added which is 55% of the target.  During the 11th Five Year Plan, capacity addition for hydro has been planned as 16553 MW, but during the first 3 months, we have not added any MW from hydro against the target of 585 MW.   There are many bottlenecks at pre- construction stage  and during the construction  stage which are responsible for  not achieving targeted capacity addition which are being dealt in this paper briefly :-

- ADMINISTRATIVE

- Delay in Providing Support by Govt. – The letters/certificates/clarifications etc. required by various agencies to prepare the proposals for various clearances of the hydroelectric projects are not provided by State Govt. timely and the delay in getting the clearances taken place which further delays the start of the project.  State Govt. has several other routine works and finds it difficult to act fast because of the prevailing lengthy system of dealing with matters in the Secretariats. Special Task Force at State Secretariat level is required to be formed by State Govt. for dealing with new hydro projects.

- Inter-state Disputes – Under the constitution of India, the water is a state subject. Many major rivers flow through more than one state and its water is being used in all such States. Unfortunately, due to political rivalry, the inter-state disputes over the sharing of river water have become almost un-resolvable.  If any activity to divert the water, to store the water or to restrict the flow of water is done in one State, the States on down-stream make hue & cry without going in details of the scheme. Due to such problems, it is becoming difficult to finalize the d/s discharge during the lean period making the operation of multipurpose reservoir a nightmare. No objection Certificate is required from each down-stream State for getting sanction even for run-of-the-river scheme which is time consuming job. If all major rivers are made National sources and its water is distributed by Centre keeping the requirement of States in mind, the time may be saved.

- Delay In Private Land Acquisition – The land acquisition for hydroelectric project is a time consuming lengthy process and is done by State Govt. according to age old Land Acquisition Act, 1894.  Unlike other industries the hydroelectric project requires land acquisition spread over vast area and lying in various districts. Thus the project management has to spend much time for liaisoning with State Govt. officials and getting completing the legal formalities by State Govt. officials. The work of identification of land, its physical verification and preparing papers for private land acquisition is done by Patwaries & Amins working under Tehsildars. They have many other routine and on demand works of State so they are unable to give due time for the work of other Agency. After preparation and duly approval of such land acquisition papers, these cases are handled in State Govt.  Secretariats and cases move in Power Department, Revenue Department, Home Department, Legal Department and then the concerned Minister and Hon’ble CM of the State for getting final approval for Section-4 Gazette / Newspaper notification. Rate fixation is another big problem as nowadays, no land holder agrees for circle rates. The land holders want maximum rates of their land and the State and local administration has lenient attitude. Then the agency taking land has to pay much more than estimated cost of land. This not only involves time but it becomes almost impossible to predict when the possession of private land can be obtained and at what cost.  Land Acquisition Act of 1894 needs replacement by new Act making the provisions easier and less time consuming. Special Task Force made at State Secretariat may be made responsible for private land acquisition for Hydroelectric Projects in the State.

- Law & Order / Militancy Problems – Most of the Hydroelectric Projects are constructed in hills or on foothills. In hills at many places, local people have their own law and custom   and they do not deviate from it. They do not follow the State’s law prevailing in most part of the State. Whenever, any activity is started in such area, local people create many problems, close the path, beat the labourers and sit on dharnas. State Machinery takes much time to help in such situations.  Some parts of the country are infested with various militant outfits. These organizations frequently declare long bundhs and massacre innocent people. Due to these frequent bundhs and fearful atmosphere, the transportation network is completely paralyzed making the movement of man & material difficult and erratic. Due to uncertainty in supply of material, the forced idleness of the manpower increases. Special Task Force of local administration may be made by the State as soon as the agency desires to start activities for construction of Hydroelectric Project.

- Lack of Support of State Authorities – Even after obtaining all statutory  clearances and implementing all measures suggested by various agencies while according clearances sincerely and honestly by the hydropower development agency, some state authorities/political parties/local leaders create problems during construction of the project and thus time and cost over run starts adding up. Special task force suggested at secretariat level and local administrative level for development of Hydropower projects may take care such problems.

- Non Provision of Employment for fully Project Affected Families – Now a days in R&R plan of hydroelectric project there is no provision for employment to any person of fully project affected families. Even N.P.R.R. does not advocate such employment. When fully affected family looses its land for the construction of the project, it looses its bread & butter also. Such family expects employment of at least one person in such project. The local population wants employment in project and pursue for the same from start of S&I work till its commissioning. When the employment to one person of fully project affected family is not given, the local people with the support of local leadership create many problems during construction and after commissioning also. Thus project looses many working mandays and time & cost over run takes place. It is seen that whenever employment is given to one person of a fully project affected family that family remains always  grateful and loyal to the project , supports and praises the project at all occasions and always speaks good about the company among its relatives, friends and neighbourers. Therefore hydroelectric developing agencies may keep provision of employment to one person for fully project affected family in its R&R plan.

- PLANNING RELATED ISSUES

- Haphazard Hydropower Development of Basin – The Projects should be conceived as a part of Basin Development Plan otherwise some projects will make other projects unviable, inefficient and under capacity. The State Govt.’s Task Force meant for hydropower development and Central Govt.’s agencies like CEA & CWC may take care such aspects.

- No System to Decide the Sequence of Construction of Project in a Basin – There is adhocism in the development of hydroelectric projects with the result that sometimes projects in upper reaches are undertaken much before the development in lower reaches takes place with the result, the cost of infrastructure development becomes very high and has to be borne solely by the projects in the upper reaches. A master plan for the development of entire basin should be formulated which should also indicate the sequence of development of the hydroelectric projects in that basin so that infrastructure development can also be planned accordingly. The State Govt.’s Task Force and Central Govt.’s Agencies may take care such aspects.

- CONSTRUCTION ISSUES

- Lack of Updation of Technical Development - Many developments in infrastructure construction are being taken place throughout the world. For speedy, economical and quality construction, updation of knowledge about such new developments is essential. While awarding  contracts to foreign agencies, it should be ensured that  transfer of technology programme forms  part of agreement so that  Indian Engineers can get training for new technologies, make aware  themselves  about new developments and see the physical implementation of new technology  at-site. In India also the engineers should be allowed to visit as many hydroelectric projects under construction stage as possible so that they can acquaintance themselves with the problems faced, causes of problems and solution sought besides the new construction methodology adopted and new technology introduced, if any. Govt. P.S.Us. and big private sector companies should also ensure at least fifteen days foreign visit per two years for their Engineers for the updation of latest technological  development in construction industry.

- Dearth of Competent Indigenous Construction Agencies – There is a dearth of competent contracting agencies having sufficient technical, managerial construction and financial resources required for undertaking mega hydroelectric projects. This was due to absence of construction market in the near past, large enough to develop such competent contracting agencies. While civil construction industry was able to survive and flourish due to construction boom in middle east and far east, the problem is very acute in hydro-mechanical and electromechanical industry where due to stagnant market during eighties and nineties a large number of public sector and private sector units have closed their establishment and their technical manpower well experienced in design, construction and erection have been retrenched. Not more engineers have been recruited in this industry for a long time and the firms are finding difficult to get design, construction and erection professionals. Now from last five year plan, construction boom has come in infrastructure construction industry including power sector so Indian companies are making joint venture / consortium with foreign companies and with such partnerships manpower development in design, construction and erection is taking place.

- Lack of Adequate Experienced Construction Manpower (Technical and Managerial) – Due to thrust on short term targets, practically there was no development in hydropower sector barring the CPSUs during eighties and nineties, due to which the entire generation of engineers in state sector has gone without work experience and now when work has picked up, suitably experienced technical and managerial manpower at senior level is not available adequately and there is much poaching of manpower at senior level. This is true for the entire construction industry but more so in hydropower sector and construction of Hydro Power industry are facing a lot of problems in arranging the experienced construction engineers. Many engineering colleges and Diploma polytechnics are introducing exclusive Hydropower courses which may help in sorting out such problems upto some extent in near future.

- Geological Surprises – The Himalayan range is of recent origin and therefore it is geologically quite active. However, elaborate the subsurface exploration is, the geological surprises cannot be avoided with the result that planning of construction methodology becomes infractions and much time and money is required in changing the construction equipment and methodology to overcome such problems during construction. The contractor is resistant to deploy sophisticated equipment to adopt new technique and to shift for other methodology but, prefer to work with versatile equipment which are slow and inefficient thus the construction time and cost increases. By giving more time and money for sub-surface investigation works, deploying latest technology for comprehensive study of rocks and by using the Geo-physics development during preconstruction and construction stage may reduce the probability of geological surprises.

4. CLEARANCES

(a) Waiving of TEC – As per Electricity Act 2003, TEC is not required for Thermal Plants but for Hydro Plants having capacity more than 100 MW needs TEC. TEC is a cumbersome time consuming process and is accorded by CEA. The role of CWC may be to examine whether project is compatible or not with its river management plan. The economic aspect may be left to the financiers and developers. Examination of technical feasibility and safety of structures for major projects (> 250 MW) can be retained by CWC/GSI. C.E.A. may act as coordinator to monitor basin wise development of Hydropower of entire country.

(b) Environmental and Forest Issues

(i) No Authority with State Forest Department for Allowing Initial S&I Works – At present Stage-I clearance is given by MOEF, GOI which takes time. If the State Forest department is authorized to allow initial Survey & Investigation works, a lot of time can be saved. If the Hydropower developing agency finds project commercially viable, the State Forest Department may be authorised to give permission for development of infrastructure in forest land like construction of approach roads, bridges etc.

(ii)	 Environment & Forest Clearance – On the recommendation of Environment Appraisal Committee, environment clearance is accorded by MOEF on the basis of EIA/EMP made by another agency and public hearings conducted by State Pollution Control Board. Here NGOs having anti dam and anti hydro development attitude create a lot of uncalled for problems. As per Forest Conservation Act 1980 Forest land diversion, above 40 hec. requires approval of MOEF GOI on the recommendation of State Forest Department. After approval of Forest land diversion, the agency has to make payment of handsome amount of N.P.V. as per Hon’ble Supreme Court order. Even after making N.P.V. payment, the agency has to pay the cost of compensatory afforestation Catchment Area Treatment, leased rent etc to State Forest Department. State Forest Department also desires to put maximum amount for Catchment Area Treatment plan, over and above the guidelines provided by MOEF Govt. of India otherwise Forest land diversion proposal is not recommended to MOEF GOI. Special Task Force at State Secretariat level may take care such type of problems.

5. COST RELATED ISSUES

(a)  High Cost of Roads and Bridges in Inaccessible Projects Sites – many projects are located in the high mountainous regions far away from rail head for which approach roads are to be developed. At present, the cost of road development is borne by the hydroelectric projects which increases the construction cost of the project and thereby high tariff. Since the construction of new roads, bridges and upgradation of roads boost the overall development of the region, the cost of the roads and bridges may be shared by M.O.S.T., State PWD etc. As the construction of hydroelectric projects has gained importance due to worsening power crisis, the road development plan of M.O.S.T., State PWDs may accommodate the requirement of hydro power sector.

(b)  High Cost of Security – Due to poor law & order and militancy condition in various parts of the country, heavy security arrangement has to be provided by the State for which cost is being borne by the project. As the law and order is the responsibility of the State, the cost of security may be borne by the State/Centre.

(c)  Royalty – Since the hydroelectric projects provide 12% free power to State, the royalty on quarry material can be exempted.

(d) Custom Duty for Hydro Projects – There is relief in custom duty for imported equipment and machinery for mega projects. For all hydroelectric projects the custom duty may be exempted for imported equipment and machinery.

(e)  Tax Holidays – As huge finance is required to establish any hydroelectric project hence State Govt. and Central Govt. both may consider tax holidays for the hydropower development agencies for at least 10 years after declaration of commercial commissioning of the whole project.